## Sheet1
| start | end
Semester 1
Dataset preparation | 9.15 | 9.22
Detector
Detector design | 9.22 | 10.27
Train and improve detector | 9.29 | 10.27
Recognizer
Recognizer design | 10.27 | 11.24
Train and improve recognizer | 11.3 | 11.24
Integration
Integrate recognizer and detector | 11.24 | 12.1
Report
Prepare Gantt chart | 9.27 | 9.29
Write progress report | 11.03 | 11.10-
Prepare progress presentation | 11.10- | 11.17
Semester 2
Model Deployment | 1.19 | 2.9
Testing and debugging | 2.9 | 2.23
Report
Write final report draft | 2.23 | 3.9
Write final report | 3.9 | 4.13
Prepare final presentation | 3.9 | 3.23
Prepare poster | 4.6 | 4.13